## GUIDE >Project Delivery Process
CANAL STRATEGY DELIVERY SCHEDULE
PROJECT IDENTITY |  | VALIDATE & ESTABLISH |  | COLLABORATE | DEVELOP | INCORPORATE
A project is tabled that has a broad starting cost and basis for meeting strategic goals |  | Validate the project within the Canal Strategy by using the Project Description (the ingredients) and Placemaking Framework (the Canal Districts). Also validate the project outcomes according to the Relative Grading tools (Tab 1 - project parameters) to identify strategic outcomes potential for Canal Strategy and key starting points (costs, project lead) for ongoing planning. | Establish the role of SDC as Encourager, Enabler or Leader in developing the project when a new project comes to light or is identified, based on initial scoping and validation. | Ascertain project lead organisation and any collaborative opportunities from throughout the Canal district (or beyond). Refer to Evidence Base Summary for stakeholder engagement and innovative opportunities | Discuss need, delivery and sustainability opportunities and considerations whilst the project is in its infancy and in order to inform making the case for the project; and make plans to review during the project. | Outline any post-delivery opportunities, monitoring and observations/potential for learning, for inclusion into the District Placemaking Framework and Canal Strategy literature; and which can be applied to future project development within the Canal Strategy.
| Securing Funding. Rooting a project business case in the Canals Vision and Strategy | (a) Does the project already have financial resources from anyone? (b) Does the project have any ‘in kind’ resources available to it? Can these be valued? (potential for matched funding). | (a) Is the project fully funded or is there a funding gap? (b) Is there a role for SDC in facilitating closing the funding gap (NOTE 1) | If the project is already funded and there is potential for collaboration – see NOTE 3 If the project is already funded and collaboration is unrealistic – see NOTE 4 If the project is unfunded or there is a funding gap (and potential for collaboration) – see NOTE 5 | (a) Develop the financial plan for the project; and its ongoing sustainability if appropriate (b) Develop any associated funding applications | (a) Identify any opportunities for building on existing activities should future funding become available (b) Identify learning from financial packages and performance to date
| Cumulative Opportunity: Using the Canal Vision and Strategy to optimise funding eligibility and spending by coordinating collective objectives across projects or themes or geography | (a) Is there a clear project lead? Or can a lead be easily identified? (public/private/ Community/voluntary Sector) (b) Is the project proposed from a single organisation or a partnership? If the latter, who are the partners | (a) Can the project be linked to any other projects already known about in the same Canal District? In another canal district? Across a common theme? (NOTE 2) (b) Does SDC need to lead or facilitate securing a lead partner and/or a project partnership? |  | (a) Develop the project partnership and delivery roles and responsibilities, agreements, coordination, reporting, monitoring processes etc | (a) Identify partnerships which can continue to support future projects (b) Identify learning from partnership development and delivery for future project benefit
| Vision and Strategy application | What drivers in the Canal Strategy does this align to? What Canal Districts are involved? | What ingredients does the project align to? |  |  | What can we learn about which ingredients are best applied in different Canal Districts and how they work, to inform future project activity
A funding opportunity is available for any new project provided it meets certain criteria. e.g. the criteria could be cost-specific, meet social outcomes or environmentally sound. |  | Validate the idea/potential within the Canal Strategy by using the Project Description (the ingredients) and Placemaking Framework (the Canal Districts). Also validate the project outcomes according to the Relative Grading tools (Tab 1 - project parameters) to identify strategic outcomes potential for Canal Strategy and key starting points (costs, project lead) for ongoing planning. | Establish the role of SDC as Encourager, Enabler or Leader in developing a project when a new opportunity comes to light or is identified, based on initial scoping and validation. | Ascertain potential to identify a likely project lead and/or collaborative and partnership opportunities from throughout the Canal district (or beyond) based on the potential of ideas to develop into viable projects. Refer to Evidence Base Summary for stakeholder engagement and innovative opportunities | Develop and refine ideas into viable projects delivering Canal relevant outcomes. Discuss any delivery opportunities and considerations whilst the project is in its infancy and make plans to review during the works. | Outline any post-delivery opportunities and observations for inclusion into the District Placemaking Framework and Canal Strategy literature
| Securing Funding. Rooting a project business case in the Canals Vision and Strategy | (a) For any new funding source being considered - check details of eligibility to establish potential for use. (b) What is the realism of there being any financial resources to support the idea if it can be developed into a project - either from proposers/supporters or externally | (a) Is it realistic to consider a financial package could be assembled? (b) is there a need for SDC to lead or facilitate further investigation of potential new funding sources? | If the project could potentially have its funding available – see NOTE 6 If the project is unfunded or there is a funding gap – see NOTE 5 | (a) Develop the financial plan for the project; and its ongoing sustainability if appropriate (b) Develop any associated funding applications | (a) Identify any opportunities for building on existing activities should future funding become available (b) Identify learning from financial packages and performance to date
| Cumulative Opportunity: Using the Canal Vision and Strategy to optimise funding eligibility and spendingby coordinating collective objectives across projects or themes or geography | (a) Can a potential project lead be easily identified? (public/private/ Community/voluntary Sector) (b) Will it need or should it develop as a project partnership? If the latter, who needs to be included as partners? | (a) Can the idea be linked to or build on any other projects already known about in the same Canal District? In another canal district? Across a common theme? (NOTE 2) (b) Does SDC need to lead or facilitate securing a lead partner and/or a project partnership? | Aim to take a partner co-production/design approach to developing project idea and partnerships | (a) Develop the project partnership and delivery roles and responsibilities, agreements, coordination, reporting, monitoring processes etc | (a) Identify partnerships which can continue to support future projects (b) Identify learning from partnership development and delivery for future project benefit
| Vision and Strategy application | What drivers in the Canal Strategy does this align to? What Canal Districts are involved? | What ingredients does the project align to? |  |  | What can we learn about which ingredients are best applied in different Canal Districts and how they work, to inform future project activity

## NOTES >Project Delivery Process
CANAL STRATEGY DELIVERY NOTES:
Note 1: | Possible ways in which SDC could help in closing a funding gap:
• Through the planning process e.g. use of biodiversity net gain potential; links with green infrastructure initiatives; use of CIL/S106 agreements; building canal benefits into planning applications where appropriate and feasible
• Through procurement – social value outcomes
• Through linking any inward investment activities with GFirst LEP, to achieving potential canal benefits
• Through wider work with potential investors/investing organisations (e.g. banks, including those with social intentions eg Triodos Bank)
• Through direct support in developing third party funding applications; or crowd funding pitches
• Through direct financial contributions to a project
• Through making SDC funding applications where appropriate
Note 2: | Potential for linking activities; for example:
• Linking across ingredients:
– is there potential to use the planning process to bring different ingredients together
– are there other ways in which ingredients can be linked together to create a more comprehensive approach? Linking within their wider groupings (e.g. green infrastructure and biodiversity, infrastructure and utilities) as well as across the wider groupings (e.g. Movement and Green Infrastructure)
– Linking across themes – is there potential to link using the three Canal Visions themes of crossings, clustering, connections
– Is there potential to link across time horizons - can any short term and longer term projects be combined?
– Is there potential to link projects with common types of partners or within the same partnership?
Note 3: | Project is funded and there is potential for collaboration – points to consider:
| Can collaboration be achieved within known timescales attached to the funding? |  | Can additional funding accommodate additional elements arising from collaboration?
| NO | YES |  | NO
| Is there any scope to influence the project as it stands in order to gain more Canal-related benefit? |  | Can existing funding act as a match for a larger project?
Potential exists for a greater and more collaborative project -
BUT is it still deliverable within the timescales?
Note 4: | Project is funded but collaboration is not feasible:
• Test whether there is any scope to influence the project as it stands, to gain more Canal-related benefit
Note 5: | Project is unfunded or there is a funding gap; points to test:
| 1. Is there a project partnership/lead | YES | 2. Can a sound case for the project be made, based on evidenced need and the potential for financial sustainability long-term?
Scoping external funding potential:
NO
|  |  |  | YES | 3. What might the funding opportunities be that accord with the project intentions - from partners, from investors, from external funding sources? | Review funding guide e.g. Funding Opportunties Bulletin and Gloucestershire Voluntary and Community Sector Alliance (also see Funding Opportunities Tab):
| Can a project lead (and partnership, if appropriate) be assembled? | YES
• are there any changes or adjustments that might need to be made to the project to achieve a fit with any funding?
| NO |  | NO
| Is it realistic to progress? | NO | With further research and development, could this be achieved? | YES |  | • are changes or adjustments acceptable? The principle should be one of NOT manipulating projects to fit funding streams.
Or 'park' as an idea?
Note 6: | Potential for new funding opportunities to support new project ideas - points to test
• What is the project idea; how does it fit the Canal Strategy and deliver appropriate outcomes?
• Are the ideas and outcomes ones that have a fit with the possible new source of funding?
• Are there any adjustments that might need to be made to the project idea, to achieve a fit with any funding?
• Are adjustments accceptable. The principle should be one of not manipulating projects to fit funding streams
• Does the developing project have champions and buy in? Without these it may not succeed through development stages.
• Does the project still conform with original vision and objectives after changes?
• Are there any time risks/dependencies associated with any project adjustments made? And with the new funding source? Are these acceptable/compatible?

## GLOSSARY >Project Delivery Proc
GLOSSARY
COST THRESHOLDS (AS OF NOVEMBER 2021) | Low | An estimated project delivery cost indicated in Pounds Sterling totalling up to £250,000
| Medium | An estimated project delivery cost indicated in Pounds Sterling totalling between £250,000 and £1,000,000
| High | An estimated project delivery cost indicated in Pounds Sterling totalling over £1,000,000
SDC role: | Leader | SDC has the most collaborative responsibility for a project that is valid in the Canals Strategy, and strives to set the standards for its successful implimentation
| Enabler | SDC has a shared responsibility and influence in partnerships and projects, and sometimes as a facilitator to the projects in the Canals Strategy
| Encourager | SDC has only an indirect influence and can provide information and incentives to encourage behaviours and strategies that make positive contributions towards the Canals Strategy
Carbon Footprinting Canal Areas | A Consumption Based Approach | This analysis is based on a consumption-based approach to carbon footprinting and uses data from the Impact Tool, an online carbon calculator tool produced by the Centre for Sustainable Energy in partnership with the University of Exeter and with funding from the Department of Business, Energy and Industrial Strategy (BEIS) and the UKRI Strategic Priorities Fund.
| Per Strategy Area | This consumption-based approach to carbon footprinting relies on data at household or address-level that is then aggregated in order to estimate a footprint size for a given geography (e.g. a parish, ward, LSOA etc.). In this case, the data has been aggregated to provide a separate community-scale carbon footprint for each of the fourteen defined areas along the canal.
| Categories of Carbon Emissions | This type of carbon footprint considers the way in which residents live, and includes upstream and downstream emissions associated with the consumption of goods and services. The analysis divides consumption emissions into five categories: Housing Travel Food and diet Other goods and services Waste
A detailed methodology paper outlining the calculation process and sources of data can be found on the Impact Tool website here: https://impact-tool.org.uk/static/doc/Impact-methodology-paper-v1.6.pdf.
Carbon Reduction Opportunity | Per Strategy Area | Define
Emissions Categories
Social Outcomes | SDC Social outcome measures:
| Themes | Adopted SDC TOMs
Outcomes
Measures
2030 Strategy cross referencing | 1-13 Themes | The 13 strategy themes described in "The 2030 Strategy" by Stroud District Council (Autumn 2020). These include 7 themes providing context and 6 cross-cutting themes that provide the scope for action

## Project parameters
Ref | Project Description | Type |  |  | RELATIVE GRADING
|  |  | Delivery term |  | Carbon reduction opportunities |  |  |  |  | Social outcomes |  |  |  |  | Cost threshold | Cost Notes: Project scaleable between L-M-H thresholds? Y / N | Strategy 2030 themes (7)
|  |  | Implemented | Completed | Project contributes to opportunities to reduce carbon: |  |  |  |  | Project contributes to Social Value Themes: | [6 empty] | Project contributes to 2030 Strategy Themes: | [6 empty] | 2030 Strategy Key Priorities Projects primarily contribute to:
[5 empty] | Housing | Travel | Food & Diet | Other Goods & Services | Waste | Jobs | Growth | Social | Environment | Innovation |  |  | Energy | Built Environment | Natural Environment | Mobility | Our Economy | Waste & Resources | Community
| Project Description | Type | SORT | SORT | SORT |  |  |  |  | SORT |  |  |  |  | SORT
1 | Signposting, Navigation & Trail finding | Movement | Low Hanging | Low Hanging | [6 empty] | ✔ |  |  | ✔ | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
2 | Lighting | Movement | Low Hanging | Low Hanging | [6 empty] | ✔ | ✔ |  |  | LOW | Y - upwards | [7 empty] | E:Mainstream Renewables
3 | Connections and Interchanges | Movement | Medium | Medium | [5 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | MEDIUM | Y - upwards | [7 empty] | M:Accelerate Modal Shift
4 | Pride in Public Transport | Movement | Low Hanging | Long | [5 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | HIGH | N | [7 empty] | M:Accelerate Modal Shift
5 | Less Cars - More People | Movement | Low Hanging | Long | [5 empty] | ✔ |  |  | ✔ | ✔ | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
6 | Accessible Townscape | Movement | Medium | Medium | [5 empty] | ✔ | ✔ |  | ✔ | ✔ | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
7 | Prioritise Active Travel | Movement | Meanwhile | Short | [5 empty] | ✔ |  | ✔ | ✔ | ✔ | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
8 | Park and Move | Movement | Meanwhile | On-going | [5 empty] | ✔ |  | ✔ | ✔ | ✔ | HIGH | Y - downwards | [7 empty] | M:Accelerate Modal Shift
9 | Reclaim Roads | Movement | Medium | Long | [8 empty] | ✔ | ✔ | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
10 | Connecting the Banks | Movement | Low Hanging | Medium | [5 empty] | ✔ | ✔ |  | ✔ | ✔ | LOW | Y - upwards | [7 empty] | E: Detail the Vision
11 | Walking on Water | Movement | Low Hanging | Short | [6 empty] | ✔ |  | ✔ |  | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
12 | Future Canal Building Interfaces | Urban Form | Short | Long | [8 empty] | ✔ |  | LOW | Y - upwards | [7 empty] | W:Communicate the Waste Hierarchy
13 | Future Canal Building Typologies | Urban Form | Medium | Medium | [5 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | MEDIUM | Y - upwards | [7 empty] | BE: Retrofit Challenge
14 | Canal Gateways & Landmarking | Urban Form | Low Hanging | Medium | [10 empty] | LOW | Y - upwards | [7 empty] | BE: Retrofit Challenge
15 | Flanking the Canal | Urban Form | Medium | Medium | [6 empty] | ✔ |  |  |  | MEDIUM | Y - u & d | [7 empty] | E:Mainstream Renewables
16 | Urban & Rural Identities & Transitions | Urban Form | Medium | Horizon | [5 empty] | ✔ |  |  |  | ✔ | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
17 | Canal Side Living | Uses & Activity | Short | Medium | [7 empty] | ✔ | ✔ | ✔ | MEDIUM | Y - upwards | [7 empty] | BE: Retrofit Challenge
18 | Canal Side Enterprise | Uses & Activity | Medium | Long | [5 empty] | ✔ | ✔ |  | ✔ | ✔ | LOW | Y - upwards | [7 empty] | E: Detail the Vision
19 | Canal Hub: Cultural & Social | Uses & Activity | Meanwhile | On-going | [6 empty] | ✔ | ✔ |  | ✔ | LOW | Y - upwards | [7 empty] | E: Detail the Vision
20 | Diversify Activity | Uses & Activity | Short | Long | [5 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | LOW | Y - upwards | [7 empty] | E: Detail the Vision
21 | Floats my Boat | Uses & Activity | Low Hanging | Short | [5 empty] | ✔ | ✔ | ✔ |  |  | LOW | Y - upwards
22 | Public Art | Uses & Activity | Meanwhile | On-going | [6 empty] | ✔ |  |  |  | LOW | Y - upwards | [7 empty] | C:District Dialogue
23 | Residential Moorings | Uses & Activity | Low Hanging | On-going | [5 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | LOW | Y - upwards | [7 empty] | M:Accelerate Modal Shift
24 | Linking Canopy | Green Infrastructure & Biodiversity | Low Hanging | Horizon | [6 empty] | ✔ |  | ✔ | ✔ | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
25 | Multi-functional, Canal Side Public Realm | Green Infrastructure & Biodiversity | Short | Long | [5 empty] | ✔ | ✔ | ✔ |  | ✔ | MEDIUM | Y - u & d | [7 empty] | M:Accelerate Modal Shift
26 | Canal Hub: Connecting with Nature | Green Infrastructure & Biodiversity | Low Hanging | Short | [6 empty] | ✔ |  |  | ✔ | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
27 | Building for Nature Interventions | Green Infrastructure & Biodiversity | Low Hanging | Medium | [5 empty] | ✔ |  |  |  | ✔ | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
28 | Natural Wayfinding | Green Infrastructure & Biodiversity | Short | Medium | [5 empty] | ✔ | ✔ | ✔ |  |  | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
29 | Canal Habitats & Species | Green Infrastructure & Biodiversity | [21 empty] | NE:Embed Holistic Approach
30 | Wild Banks | Green Infrastructure & Biodiversity | [21 empty] | NE:Embed Holistic Approach
31 | Carbon Sequestration | Infrastructure & Utilities | Medium | Horizon | [5 empty] | ✔ |  |  | ✔ | ✔ | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
32 | Energy Generation | Infrastructure & Utilities | Short | Long | [5 empty] | ✔ |  |  | ✔ | ✔ | MEDIUM | Y - u & d | [7 empty] | E:Mainstream Renewables
33 | Pride in Innovation & Quality | Infrastructure & Utilities | Short | Long | [8 empty] | ✔ | ✔ | MEDIUM | Y - u & d | [7 empty] | E: Detail the Vision
34 | Water Management | Infrastructure & Utilities | Short | Long | [9 empty] | ✔ | MEDIUM | Y - u & d | [7 empty] | NE:Embed Holistic Approach
35 | The Seasonal Canal | Events, Programmes | Low Hanging | On-going | [6 empty] | ✔ | ✔ |  | ✔ | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
36 | Our Canal | Events, Programmes | Short | On-going | [6 empty] | ✔ | ✔ |  | ✔ | LOW | Y - upwards | [7 empty] | E: Detail the Vision
37 | Social Prescribing | Events, Programmes | Low Hanging | On-going | [5 empty] | ✔ | ✔ | ✔ |  |  | LOW | Y - upwards | [7 empty] | C:District Dialogue
38 | The Classroom Corridor | Events, Programmes | Short | On-going | [5 empty] | ✔ | ✔ | ✔ | ✔ |  | LOW | Y - upwards | [7 empty] | NE:Embed Holistic Approach
39 | Canal Branding & Marketing | Events, Programmes | Low Hanging | On-going | [5 empty] | ✔ |  | ✔ | ✔ | ✔ | MEDIUM | Y - u & d | [7 empty] | E: Detail the Vision
40 | Varied events on vacant sites/space | Events, Programmes | Meanwhile | On-going | [5 empty] | ✔ | ✔ | ✔ |  | ✔ | LOW | Y - upwards | [7 empty] | W:Communicate the Waste Hierarchy
2030 Strategy Key Priorities:
Energy: Mainstream Renewables
Built Environment: Retrofit Challenge
Natural Environment: Embed Holistic Approach
Mobility: Accelerate Modal Shift
Economy: Detail the Vision
Waste: Communicate the Waste Hierarchy
Community: District Dialogue
£

## Social Value Themes & Outcomes
|  |  | Jobs: Promote local skills & employment | [6 empty] | Growth: Supporting Growth of Responsible Regional Business | [6 empty] | Social: Healthier, Safer and more Resilient Communities |  |  |  |  | Environment: Decarbonising and Safeguarding our World | [5 empty] | Innovation: Promoting Social Innovation
Ref: | Project Description | Type
|  |  | More local people in employment | Fair Work | More opportunities for disadvantaged people | Improved skills | Improved skills for disadvantaged people | Improved skills for a low carbon transition | Improved employability of young people | More opportunities for local MSMEs and VCSEs | Improving staff wellbeing and mental health | Reducing inequalities | Ethical Procurement is promoted | Cyber security risks are reduced | Social Value embedded in the supply chain | Supporting workers, SMEs and VCSEs to face the COVID-19 crisis | Crime is reduced | Creating a healthier community | Vulnerable people are helped to live independently | More working with the Community | Supporting communities to deal with the COVID-19 crisis | Carbon emissions are reduced | Air pollution is reduced | Safeguarding the natural environment | Resource efficiency and circular economy solutions are promoted | Sustainable Procurement is promoted | COVID-19 environmental response | Social innovation to create local skills and employment | Social innovation to create local skills and employment | Social innovation to enable healthier safer and more resilient communities | Social innovation to safeguard the environment and respond to the climate emergency
| Project Description | Type
1 | Signposting, Navigation & Trail finding | Movement
2 | Lighting | Movement
3 | Connections and Interchanges | Movement
4 | Pride in Public Transport | Movement
5 | Less Cars - More People | Movement
6 | Accessible Townscape | Movement
7 | Prioritise Active Travel | Movement
8 | Park and Move | Movement
9 | Reclaim Roads | Movement
10 | Connecting the Banks | Movement
11 | Walking on Water | Movement
12 | Future Canal Building Interfaces | Urabn Form
13 | Future Canal Building Typologies | Urabn Form
14 | Canal Gateways & Landmarking | Urabn Form
15 | Flanking the Canal | Urabn Form
16 | Urban & Rural Identities & Transitions | Urabn Form
17 | Canal Side Living | Uses & Activity
18 | Canal Side Enterprise | Uses & Activity
19 | Canal Hub: Cultural & Social | Uses & Activity
20 | Diversify Activity | Uses & Activity
21 | Floats my Boat | Uses & Activity
22 | Public Art | Uses & Activity
23 | Residential Moorings | Uses & Activity
24 | Linking Canopy | Green Infrastructure & Biodiversity
25 | Multi-functional, Canal Side Public Realm | Green Infrastructure & Biodiversity
26 | Canal Hub: Connecting with Nature | Green Infrastructure & Biodiversity
27 | Building for Nature Interventions | Green Infrastructure & Biodiversity
28 | Natural Wayfinding | Green Infrastructure & Biodiversity
29 | Canal Habitats & Species | Green Infrastructure & Biodiversity
30 | Wild Banks | Green Infrastructure & Biodiversity
31 | Carbon Sequestration | Infrastructure & Utilities
32 | Energy Generation | Infrastructure & Utilities
33 | Pride in Innovation & Quality | Infrastructure & Utilities
34 | Water Management | Infrastructure & Utilities
35 | The Seasonal Canal | Events, Programmes
36 | Our Canal | Events, Programmes
37 | Social Prescribing | Events, Programmes
38 | The Classroom Corridor | Events, Programmes
39 | Canal Branding & Marketing | Events, Programmes
40 | Varied events on vacant sites/space | Events, Programmes

## 2030 Strategy Themes & Commitme
|  |  |  | Energy | [9 empty] | Built Environment | [12 empty] | Natural Environment | [11 empty] | Mobility | [8 empty] | Our Economy | [7 empty] | Waste & Resources | [8 empty] | Community
| Ref: | Project Description | Type
|  |  |  | Exemplar |  |  |  | Enabler |  |  |  |  | Encourager | Exemplar |  |  |  | Enabler | [6 empty] | Encourager |  | Exemplar |  |  |  | Enabler | [6 empty] | Encourager | Exemplar |  |  | Enabler |  |  |  | Encourager |  | Exemplar |  |  | Enabler |  |  |  | Encourager | Exemplar |  |  |  |  | Enabler |  |  | Encourager | Exemplar |  |  |  |  | Enabler | [5 empty] | Encourager
|  |  |  | E1 | E2 | E3 | E4 | E5 | E6 | E7 | E8 | E9 | E10 | BE1 | BE2 | BE3 | BE4 | BE5 | BE6 | BE7 | BE8 | BE9 | BE10 | BE11 | BE12 | BE13 | NE1 | NE2 | NE3 | NE4 | NE5 | NE6 | NE7 | NE8 | NE9 | NE10 | NE11 | NE12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M9 | M10 | EC1 | EC2 | EC3 | EC4 | EC5 | EC6 | EC7 | EC8 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C13
|  |  |  | Renewable Tariff | On-Site Renewables | Housing Stock Renewables | Land for Renewables | Energy Networks | Planning Policy | Planning Constraints | Community Energy | Alternative Renewables | Signposting | Efficiency Programme | Low Carbon Pathfinding | Energy awareness at work training | Heritage case study: the Museum in the Park | Financing through development | New development | Homes | Businesses | Enforcement | Neighbourhood Plans | Market Town Regeneration | Awards and incentives | Support the take-up of renewable home energy systems and green tariffs | Our Land Management | Strategy for adaptation and mitigation | Joined up working | Using our land | Planning Standards | Natural Capital | Nature Recovery | Funding for Nature | Canal Restoration | Flood Management | Tree Planting | Habitat Demonstration | Staff Travel | On-site Infrastructure | Contractors | Community Transport | Settlement Planning | Active Travel | Strategic Working | Nudges and Incentives | Awareness | Procurement Practice | Shorter Supply Chains | Ethical Investments | Infrastructure (including digital) | Low Carbon Growth | Skills | Practice Standards | PromotingLocal | Procurement | Reuse | Reduce and Refuse | Recycle | Policy & Practice | Targeted Reductions | Commercial and Agricultural Waste | Funding Schemes | Messaging | Corporate Development Plan | Quality Systems | Monitoring and Reporting | Social Return on Investment | Staff Training | Governance | Funding | Pledge | Diversity and Inclusion | Lifelong Learning | Arts and Culture | Messaging | Incentivising
|  | Project Description | Type
2 | 1 | Signposting, Navigation & Trail finding | Movement
3 | 2 | Lighting | Movement
4 | 3 | Connections and Interchanges | Movement
5 | 4 | Pride in Public Transport | Movement
6 | 5 | Less Cars - More People | Movement
7 | 6 | Accessible Townscape | Movement
8 | 7 | Prioritise Active Travel | Movement
9 | 8 | Park and Move | Movement
10 | 9 | Reclaim Roads | Movement
11 | 10 | Connecting the Banks | Movement
12 | 11 | Walking on Water | Movement
13 | 12 | Future Canal Building Interfaces | Urban Form
14 | 13 | Future Canal Building Typologies | Urban Form
15 | 14 | Canal Gateways & Landmarking | Urban Form
16 | 15 | Flanking the Canal | Urban Form
18 | 16 | Urban & Rural Identities & Transitions | Urban Form
19 | 17 | Canal Side Living | Uses & Activity
20 | 18 | Canal Side Enterprise | Uses & Activity
21 | 19 | Canal Hub: Cultural & Social | Uses & Activity
22 | 20 | Diversify Activity | Uses & Activity
23 | 21 | Floats my Boat | Uses & Activity
17 | 22 | Public Art | Uses & Activity
38 | 23 | Residential Moorings | Uses & Activity
24 | 24 | Linking Canopy | Green Infrastructure & Biodiversity
25 | 25 | Multi-functional, Canal Side Public Realm | Green Infrastructure & Biodiversity
26 | 26 | Canal Hub: Connecting with Nature | Green Infrastructure & Biodiversity
27 | 27 | Building for Nature Interventions | Green Infrastructure & Biodiversity
1 | 28 | Natural Wayfinding | Green Infrastructure & Biodiversity
| 29 | Canal Habitats & Species | Green Infrastructure & Biodiversity
| 30 | Wild Banks | Green Infrastructure & Biodiversity
28 | 31 | Carbon Sequestration | Infrastructure & Utilities
29 | 32 | Energy Generation | Infrastructure & Utilities
30 | 33 | Pride in Innovation & Quality | Infrastructure & Utilities
31 | 34 | Water Management | Infrastructure & Utilities
32 | 35 | The Seasonal Canal | Events, Programmes
34 | 36 | Our Canal | Events, Programmes
35 | 37 | Social Prescribing | Events, Programmes
36 | 38 | The Classroom Corridor | Events, Programmes
37 | 39 | Canal Branding & Marketing | Events, Programmes
33 | 40 | Varied events on vacant sites/space | Events, Programmes

## Some funding opps (Nov2021)
Information gathered October/November 2021. To be treated as indicative only as schemes may be subject to change over time. This is not a comprehensive list. It covers some possible funding sources, some of which are still in development. Always check for full details/clarification/updates.
Funding/Investment opportunity | Information Source | Key priorities/main objectives | Who can apply | Application timetables (if known) | Possible fit with 'Ingredients' |  |  |  |  | Other comments
[5 empty] | Movement | uses/activities | GI/biodiversity | infra & utilities | Events, programmes
Rural Community Energy Fund | Rural Community Energy Fund - GOV.UK (www.gov.uk)…. https://www.swenergyhub.org.uk/ | Provides (non capital) funding to community organisations to establish the feasibility of a renewable energy project and develop the business plan. Aims include helping rural communities to reduce energy costs or generate income from renewable energy and reinvest this income in the local area; and promoting rural growth through the creation of jobs and volunteering opportunities. Must reduce carbon emissions. | Legally constituted community group benefitting the local community (e.g. CIC, Co-op, CIO, Town or Parish Council). Must be a community led project (+50% owned). | Two stage application process; Stage 1 = feasibility study, Phase 2 = full business plan. Applications made via regional energy hubs. There is a SW Energy Hub. |  |  |  | √ |  | This is not a grant scheme for small scale projects. It is likely projects will be of sufficient size to need planning permission; generating energy for a single building without exporting to the grid may not be eligible - intended for multiple buildings or single community buildings which will also feed into the grid. Detailed guidance available via the regional energy hub. Note the SW Energy Hub provides local capacity support for public sector and not for profit organisations on energy projects in developing community energy projects.
National Lottery Heritage Fund (NLHF) Area Based Schemes | Area-based schemes and area action plans ¦ The National Lottery Heritage Fund. https://www.heritagefund.org.uk/funding/national-lottery-grants-heritage-250k-5m | Aim of reviving economically disadvantaged areas by conserving, repairing and enhancing their distinct character for the benefit of local residents, workers and visitors. Needs to be a geography with a clear boundary that has built and/or natural features and a distinct character that is recognised either formally or informally. Described in guidance as 'schemes should aim to halt and reverse the decline of historic landscapes and townscapes by capitalising on their unique character to create attractive, vibrant, and interesting places where people want to live work, visit and invest' . Priorities for 2021-22 applications for all projects are; promote inclusion and involve a wider range of people (a mandatory outcome); boost the local economy; encourage skills development and job creation; support wellbeing; create better places to live, work and visit; improve the resilience of organisations working in heritage | Applicant has to be a partnership - of local, regional and national interests |  | √ |  | √ | √ | √ | Two stage grant application process (EOI/Development phase). Potential for grants of £250,000 to £5,000,000. Needs to have a balanced portfolio of projects across physical works and activities to engage people in the heritage. If the development stage of an application is approved, an Area Action PLan and Area Management Plan have to be produced as part of that stage, and adopted by the Partnership making the application. Community grant schemes to 3rd parties could be built into an area based project. Could be combination of capital and revenue funding. Capital funding focused on start up activities. Maintenance thereafter needs to be assured. Note also all HLF projects are expected to meet high environmental sustainability standards. All projects must show how they help mitigate against and adapt to the effects of changing climate and help nature recover.
NLHF Habitats and species | Habitats and species ¦ The National Lottery Heritage Fund | Helping nature to recover a key NLHF priority until 2024. Looking to support projects to improve knowledge and understanding of nature, and help people to access, care for and value the natural heritage. Want to support projects that will make a strategic difference to nature. See 2021-22 priorities above - apply to all projects | Done as part of the three grant programmes £3,000 - £10,000; £10,000-£250,000; or £250,000 - £5m. Small grants: not-for-profit organisations or a private owner of heritage. Grants of £10k - £250k - not-for-profit organisation, a private owner of heritage (grants up to £100,000) or a partnership. Large grants - not-for-profit organisations or a partnership led by a not-for-profit organisation. | Small grants - rolling application process. Decisions within 8 weeks of application. Medium scale - rolling programme and decisions within 8 weeks. Large grants - two stage application process (EOI and full application). | √ |  | √ | ? | √ | Could be part of landscape scale project. Could be about exploring testing and developing new ways of working. Could be about finding new ways of engaging people with nature.
NLHF industrial, heritage and maritime. Which includes canals. | Industrial, maritime and transport ¦ The National Lottery Heritage Fund | Helping people to conserve their local industrial heritage | As above | As above | √ | √ |  | ? | √
NLHF Community Heritage | Community heritage ¦ The National Lottery Heritage Fund | Researching and sharing the history of a community or of a place; projects which combine different types of heritage in a particular location. | As above | As above | √ | √ |  |  | √
National Lottery Awards for All | National Lottery Awards for All England ¦ The National Lottery Community Fund (tnlcommunityfund.org.uk) | focus on communities most impacted by Covid-19. Notes it can continue to deliver activity e.g. community needs crisis response, recovery or business as usual activity. Also seeking to support organisations to change and adapt, become more resilient to respond to new and future challenges. Aiming to build strong relationships within and between communities, improve places and spaces, help more people to reach their potential. | Voluntary or community organisations | Rolling application programme. Anticipate decisions taking about 12 weeks. | ? | ? |  |  | √ | £300 to £10,000, for up to one year. Notes high demand for funding due to pandemic impacts; and a focus on people and communities most adversely affected by Covid-19.
National Lottery Community Fund. Partnerships Programme, Reaching Communities Programme. Both schemes available in England | Partnerships ¦ The National Lottery Community Fund (tnlcommunityfund.org.uk). https://www.tnlcommunityfund.org.uk/funding/programmes/reaching-communities-england#section-2 | Can be place based or focused on a theme. Looking for projects to be people-led, strengths-based and connected (within the community). | includes voluntary and community organisations, charities, not for profit companies, CICs, schools, statutory bodies incl Town and Parish Councils. Suggests applicants should be incorporated bodies. | Rolling application programme. | ? | ? |  | ? | ? | Can be capital and/or revenue funding, organisational and activity costs.
National Lottery Community Fund. Two UK Programmes: Growing Great ideas; Bringing People Together. | Growing Great Ideas ¦ The National Lottery Community Fund (tnlcommunityfund.org.uk). https://www.tnlcommunityfund.org.uk/funding/programmes/bringing-people-together | Growing Great Ideas - focused on supporting transformational and long-term change; investing in different combinations of people, communities, networks and organisations that demonstrate an ability to seed and grow alternative systems for 21st century civil society. Bringing People Together - projects that will build stronger connections across communities, and improve the infrastructure and conditions that are needed to strengthen these connections. Projects need to work across two countries in the UK. Has some specific priorities. | As above. | Growing Great Ideas - open application programme. Initial tranche of funding open until March 2022, but more funding expected beyond that. Two stage application process - EOI/Full. | ? | ? |  | ? | ? | Growing Great Ideas - Minimum grant size is £150,000. The minimum length is two years. Funding can be available for up to ten years in some circumstances. Prioritising applications that work across the UK, although recognising that this may not always be appropriate. Bringing People Together - anticipating 20 awards in 2021 to 2022 with projects involving at least two countries in the UK. Up to £300,000 in total for up to two years. Both schemes may be beyond the scope of the Stroud Canal Framework.
(Agricultural Payments) Environmental Land Management Scheme. Covers three strands: Sustainable Farming Incentive; Local Nature Recovery, Landscape Recovery. | Environmental land management schemes: overview - GOV.UK (www.gov.uk). https://www.gov.uk/government/publications/agricultural-transition-plan-june-2021-progress-update/agricultural-transition-plan-june-2021-progress-update | Sustainable Farming Incentive: will pay farmers to manage their land in an environmentally sustainable way. A set of standards based on features (eg hedgerow) and actions required per standard, with payment based on which standards a farmer takes up. Local Nature Recovery scheme will pay for actions that support local nature recovery and meet local environmental priorities. It will encourage collaboration between farmers. Landscape Recovery scheme will support landscape and ecosystem recovery through long-term projects. The three strands of ELMs seen as an important contribution to the Government's 25 Year Environment Plan; and GHG reductions. | Sustainable Farming Incentive - Initially environmental standards will be open to farmers who are eligible under the Basic Payments Scheme. | Sustainable Farming Incentive being piloted in 2021 before it launches in 2022. Local nature Recovery - to begin pilots in 2022 with roll out in 2024. Landscape Recovery - aiming to pilot c10 projects in 2022 and roll out in 2024. | ? |  | √ | √ |  | Agricultural payments system currently in a transition phase towards a new post CAP system. A seven year transition was envisaged. As at June 2021, the first options through the Sustainable Farm Incentive are being launched and focused on soil health. The future of the LEADER rural development initiative supported through the current Rural Development Programme for England is not yet known - whether community led local development will be incorporated into the Shared Prosperity Fund or not. Annual payments
Green Recovery Challenge Fund | Government’s £40 million Green Recovery Challenge Fund opens for applications - GOV.UK (www.gov.uk). https://www.heritagefund.org.uk/funding/closed-programmes/application-guidance-green-recovery-challenge-fund-round-2 | £40 million Fund, part of the government’s wider green economic recovery and for projects that restore nature and tackle climate change. Preference for projects that create or retain jobs, create opportunities and benefits for all ages, including young people. | Environmental charities and their partners. | Launched 2020 and application round in Sept/Oct 2020. Second round April 2021. Not clear if further rounds expected. |  | √ | √ | √ |  | Useful funding reference here: https://communityenergyengland.org/pages/funding-opportunities-2#Latest%20Funding%20Opportunities
Forestry Commission - England Woodland Creation Offer | England Woodland Creation Offer - GOV.UK (www.gov.uk)…. https://www.gov.uk/government/publications/woodland-grants-and-incentives-overview-table/woodland-grants-and-incentives-overview-table#england-woodland-creation-offer-ewco | For creating new woodland. Can support payment for establishing the woodland, annual maintenance costs for up to 10 years, cost of providing recreational access.There is also an additional contribution if it delivers multiple public benefits eg flood risk, water quality. Must be for a minimum of 1 hectares. | Owner occupiers, tenants, landlords and licensors who have full management control of the land in the application. | Rolling application process. Scheme managed by the Forestry Commission |  |  | √ |  |  | A new grant scheme to support woodland creation. There are other grant schemes related to trees through the existing Countryside Stewardship Scheme - through the Woodland Support Grant which remains open in 2021. Note the Urban Tree Challenge Fund indicates that its application window has closed.
UK Shared Prosperity Fund | https://www.gov.uk/government/publications/spending-review-2020-documents/spending-review-2020. | UK SPF is the successor to EU funding for the UK. It is a fund that is still in development. The 2020 Spending Review stated that it will 'help to level up and create opportunity across the UK for people and places'. It also indicated that a portion of the Fund will be will targeted at places most in need across the UK, such as ex-industrial areas, deprived towns and rural and coastal communities. This portion of funding would have priorities of skills development and investment in people, investment in communities and place, and investment into businesses including into 'green and tech' adoption. It also indicated a second portion of to be targeted to people most in need through bespoke employment and skills programmes that are tailored to local need and supporting improved employment outcomes. The 2021 Budget and Spending Review included specific reference to '£2.6 billion for the UK Shared Prosperity Fund over the Spending Review, focused on helping people into jobs and get on in life across the UK'. | No details as yet. | EU funding spend completes in 2023. The UKSPF will begin spend in 2022-23 and ramp up to 2024-25. | ? | ? | ? | ? | ? | Government introduced the UK Community Renewal Fund in 2021, as a pilot programme to learn lessons and gain experience to input into developing the SPF. Applications to the Community Renewal Fund were made by July 2021 but decisions on which projects would be supported were only announced in November 2021. It is not clear how timescales and learning from the CRF will now work and feed into the SPF development. There were no CRF approved projects in Gloucestershire.
Commnunity Ownership Fund | Community Ownership Fund: prospectus - GOV.UK (www.gov.uk) | New £150m four year fund. Can support the purchase and/or renovation costs of community assets and amenities, subject to meeting eligibility criteria. Prospectus states 'Proposals will need to prove the value of the asset to local people and that the asset can run sustainably for the long-term benefit of the community'. Investment will only go into assets that would otherwise be lost. | Community and voluntary organisations. Must be incorporated organisations which are set up to deliver charitable purpose, social purpose or public benefit. But Local authorities and town, parish and community councils cannot apply. Assets related to statutory services are not in scope. | Application rounds being held. 2nd application round to open December 2021 and 3rd round May 2022. Eight application rounds anticipated. | ? | √ |  | √ |  | Can provide up to 50% matched funding, matching applicant's resources and funding raised. Grants generally up to £250,000. Projects need to be ready to go within 6 months of receiving funding. So requires well worked up projects.
Levelling Up Fund | Levelling_Up_prospectus.pdf (publishing.service.gov.uk). https://www.gov.uk/government/publications/levelling-up-fund-additional-documents/levelling-up-fund-frequently-asked-questions | A capital investment programme into local infrastructure and projects up to a value of £20m, across the themes of transport, regeneration and cultural assets. Local authorities can submit one bid for every MP whose constituency lies wholly within their boundary. It is targeted at areas of need. Districts are categorised as 1,2, or 3 in terms of need. Stroud District is identified as a Level 2 district. Preference will go to Priority 1 areas. Bids from Priority 2 and 3 areas will therefore need to be strong bids as this is a competitive Fund. Project deliverability, value for money and strategic fit are important assessment criteria as well as the category of need. | Open to local authorities - including District Councils (but not Town/Parish Councils). Expectation that local authorities will have consulted with local stakeholders in bid development. | The first application round has gone and the successful bids have been announced. It focused on three themes: smaller transport projects ; town centre and high street regeneration; and support for cultural and heritage assets. The timetable for the next application round is not yet known. | √ | √ |  | √ |  | An applicant can only have one successful project over the lifetime of the Fund and spend should be complete by March 2024. So Stroud District could only have one Levelling Up project. Stroud District did not have a successful application in Round 1. There is a lot of detail around applying to be considered. Capital funding only.
Caring for the Cotswold Grant scheme | Apply for Funding - Cotswolds National Landscape (cotswoldsaonb.org.uk) | Projects need to cover one or more of four themes: Conservation of habitats and species; heritage and landscape; improving access; education. | Charities, established community groups, parish councils and other non-profit organisations. Projects must be for public benefit | Current application round runs from August to October 2021. | √ |  | √ | ? | √ | Grants from £500 up to a maximum of £2,500. Specific to the Cotswolds AONB area only.
Gloucestershire Nature and Climate Fund | Gloucestershire Nature and Climate Fund seeks project manager | Glos Local Nature Partnership and Glos First LEP are establishing a fund to leverage investment in natural solutions to the ecological and climate emergencies. The Fund is seeking to lever in funds from private and public sector organisations, notably from Biodiversity Net Gain and carbon (although specifically what aspect of carbon is not indicated). (NOTE: Biodiversity Net Gain is also an opportunity available now for the Stroud Canal Framework, through planning applications, although at present it is not a mandatory requirement) | As yet there is no further information. The fund is in early stages of set up. The post of project manager for it was advertised on the Glos LNP website in Sept 2021. |  | ? |  | √ | √ | ? | Biodiversity Net Gain is set to become a mandatory requirement on planning applications in England. A tool has been developed to measure biodiversity value before and after development and a minimum net gain of 10% will be sought. BNG can be achieved onsite, offsite and through credits. It seems likely this will become mandatory by 2023. Local Nature Recovery Plans such as that being developed by Glos LNP will be important in helping to target Biodiversity Net Gain activities. Stroud DC is represented on the LNP Board through its CEO (who is there representing all local authorities).
Stroud Community Infrastructure Levy | Community Infrastructure Levy (CIL) ¦ Stroud District Council | This is a charge on new development to help fund its supporting infrastructure needs. It pays towards district wide infrastructure needs. There is also a neighbourhood element to use of CIL receipts which is paid to Town or Parish Councils. Those with an adopted Neighbourhood Development Plan (NDP) get 25% of the CIL collected for that area and those without an NDP receive 15%. | It is not an application process as such. CIL receipts are to support infrastructure investment necessary to underpin development at both strategic (district) and local (town/parish) level. Town and Parish Councils have two opportunities annually to request any funding accrued to them. |  | √ | ? |  | √ |  | There might be opportunities to link any CIL spend with taking forward Framework actions, if these also marry with development infrastructure needs. The neighbourhood portion may also be useful for local investments. Note though, that this is not large sums - the 2019/2020 CIL Annual Report indicates that the largest sums to Town/Parish Councils were c£5,000. Most were much less.
Stroud District Council Community Resilience and Wellbeing Grant | Community Wellbeing Grant ¦ Stroud District Council | Aims to reduce inequality, promote wellbeing and support community recovery post pandemic. The grant will support groups who work with their communities to reduce inequality and promote aspects of wellbeing such as physical, mental and financial health, social connection, arts, culture, heritage and the environment. | There has been an application round. Not clear if there will be a second round. |  | ? | ? | ? |  | ?
Gloucestershire Economic Growth Capital Investment Pipeline (CIP) | Project Pipeline (gfirstlep.com) | Not a grant source as such. This is the LEP's pipeline of projects seeking capital funding, which could support significant economic growth and which are seeking public investment. Priorities include innovation, regeneration and place shaping. Phases 1a and 1b of the Cotswolds Canal project are already in the pipeline, as is Brimscombe Port. | The pipeline is open to receiving new bids - but it is a pipeline and there for when funding might be available. So there is no guarantee of funding. |  | √ | √ | ? | √ |  | The key emphasis is on economic growth. The Gloucestershire Growth Deal and the EU Structural and Investment Fund Strategy have been two major funding sources to date. Some
Gloucestershire Infrastructure Investment Fund | Local and Regional Growth Funds ¦ GFirst LEP | A revolving infrastructure investment fund to stimulate local economic growth by funding infrastructure needed to unlock constrained and stalled development sites. Investment needs to generate development value, new jobs, housing and regeneration. Works on an interest free repayable loan basis. | EOIs can be submitted. A number of projects are already funded. The LEP website indicates that, as well as meeting current commitments, there may be scope to consider one or two smaller projects. |  |  | √ |  | ? |  | The emphasis is on unlocking stalled development sites. This would only be applicable to the Canal Framework, if this were applicable for a specific development. A full business investment case will need to be made.
Severn Trent Water Community Fund | Severn Trent Community Fund ¦ About Us ¦ Severn Trent Water (stwater.co.uk) | Improving community wellbeing - which can be helping people to lead a healthier life and gain new skills; creating better places to live in and use; improving the natural environment (and water) and giving people greater access to the environment. Ideally projects would fit all three aspects of people, place and environment. | Local charities and community groups | Not specifically indicated | √ | ? | √ | √ | ? | Projects need to meet community needs and have community impactss. STW notes a high number of applications for funding and suggests applicants discuss project ideas in advance of applications with them.
Other funding routes/links
Gloucestershire Local Transport Plan 2020-2041 | ltp-policy-document-final-v132.pdf (gloucestershire.gov.uk) | Relevance from a funding perspective is that priorities identified in the LTP provide the basis for future funding bids for transport. The LTP sets out it is seeking a more sustainable transport delivery model. Its introduction states 'We need to invest in transformative new public transport infrastructure, multi-modal interchange, attractive cycle links and encourage active travel. Includes geographic dimension in its 'Connecting Places Strategy'. For the Stroud area this includes seeking to encourage more cycling including leisure cycling (and the canal network noted as having more cycling potential); more active travel routes: community transport opportunities. |  |  | √ | ? |  |  |  | Policies include one for active travel in support of community health and wellbeing; supporting community/voluntary transport schemes; supporting development of the cycle network, pedestrian network and rights of way ; and supporting transport interchange hubs - including Local Interchange Hubs which are defined as; in key locations in/near rural towns or on urban residential roads or situated on dedicated cycle routes or near private car parking where sufficient demand and commercial viability exists. Local Walking and Cycling Infrastructure Plans are also in development. One for Stroud is in development.
Crowd Funding | 9 crowdfunding platforms for charities, community groups and social entrepreneurs ¦ Nesta | There are different platforms for crowd funding. Crowdfunder is one. Spacehive focuses on improving community/public spaces. Digventures focuses on heritage and archaeology projects (worldwide). (see NESTA doc for info on these). Others include GoFundMe and the JustGiving crowd funding platform. From an investment perspective, Triodos Bank operates a crowd funding platform and there are other ethical investor platforms such as Ethex. | [7 empty] | Included here as crowdfunding could be an opportunity in the context of some projects within the Canal Framework.
Community led businesses and social enterprises |  | Not a funding route as such, but included to raise the profile of the potential of community and social enterprises as a delivery route, and the various ways in which these could be established - Companies limited by guarantee, Community Interest Companies, Co-operatives and other models. Essentially the model is one of meeting social objectives with any profits reinvested in the community/people. | [7 empty] | Projects within the Canal Framework may lend themselves to community or social enterprise models, which can provide local benefit. Organisations such as Gloucestershire Rural Community Council and Gloucestershire Voluntary and Community Sector Alliance are useful references.
Enabling a Natural Capital Approach | Enabling a Natural Capital Approach guidance - GOV.UK (www.gov.uk) | This is not a grant scheme as such, rather a policy direction that could get increasingly important and could be a useful approach in the Stroud Canal Framework context. Natural capital accounting (taking account of ecosystems services) is increasingly being integrated into policy and project planning. The guidance tool referenced here has a range of links to tools and approaches that can be used, as well as explaining approaches. It could be a useful reference.
Stroud District Council Procurement Strategy 2019-2023. | final-sdc-procurement-strategy-2019.pdf (stroud.gov.uk) | Not a funding programme as such, but a possibility that the intention to secure community benefits through procurement (e.g. social value), as a key aim of the Strategy alongside commerciality, may offer opportunities for links with actions in the Canal Framework. | [7 empty] | This may be an opportunity to link agendas but needs to be seen in the context of procurement and the social value intentions that are set out in Appendix 3 of the Strategy.

## Carbon Footprinting Canal Areas
Canal district | Category | Sub-category | Carbon emissions [tCO2/yr] | Number of households | Carbon emissions [tCO2/yr/household]
Brimscombe | Housing | Mains gas | 1456.2899 | 624 | 2.3338
Brimscombe | Housing | Electricity | 706.7408 | 624 | 1.1326
Brimscombe | Housing | Oil | 515.8062 | 624 | 0.82661
Brimscombe | Housing | LPG | 37.382 | 624 | 0.059907
Brimscombe | Housing | Biomass | 28.2028 | 624 | 0.045197
Brimscombe | Housing | Coal | 51.089 | 624 | 0.081873
Brimscombe | Travel | Private | 1129.542 | 624 | 1.8102
Brimscombe | Travel | Public | 296.6181 | 624 | 0.47535
Brimscombe | Travel | Flights | 902.3587 | 624 | 1.4461
Brimscombe | Goods & services | Purchase of goods | 2423.8103 | 624 | 3.8843
Brimscombe | Goods & services | Use of services | 907.8503 | 624 | 1.4549
Brimscombe | Goods & services | Other | 911.9585 | 624 | 1.4615
Brimscombe | Food & diet | Meat & fish | 1353.7413 | 624 | 2.1695
Brimscombe | Food & diet | Other | 1183.9162 | 624 | 1.8973
Brimscombe | Waste | Waste | 154.1157 | 624 | 0.24698
Chalford | Housing | Mains gas | 929.8091 | 330 | 2.8176
Chalford | Housing | Electricity | 348.1305 | 330 | 1.0549
Chalford | Housing | Oil | 69.7315 | 330 | 0.21131
Chalford | Housing | LPG | 0 | 330 | 0
Chalford | Housing | Biomass | 19.1499 | 330 | 0.05803
Chalford | Housing | Coal | 0.44815 | 330 | 0.001358
Chalford | Travel | Private | 575.216 | 330 | 1.7431
Chalford | Travel | Public | 154.4949 | 330 | 0.46817
Chalford | Travel | Flights | 595.526 | 330 | 1.8046
Chalford | Goods & services | Purchase of goods | 1312.3036 | 330 | 3.9767
Chalford | Goods & services | Use of services | 471.2759 | 330 | 1.4281
Chalford | Goods & services | Other | 533.6379 | 330 | 1.6171
Chalford | Food & diet | Meat & fish | 718.4001 | 330 | 2.177
Chalford | Food & diet | Other | 644.2933 | 330 | 1.9524
Chalford | Waste | Waste | 79.4772 | 330 | 0.24084
Eastington | Housing | Mains gas | 121.5134 | 48 | 2.5315
Eastington | Housing | Electricity | 53.5492 | 48 | 1.1156
Eastington | Housing | Oil | 49.276 | 48 | 1.0266
Eastington | Housing | LPG | 0 | 48 | 0
Eastington | Housing | Biomass | 1.4051 | 48 | 0.029274
Eastington | Housing | Coal | 4.4815 | 48 | 0.093364
Eastington | Travel | Private | 105.453 | 48 | 2.1969
Eastington | Travel | Public | 26.5771 | 48 | 0.55369
Eastington | Travel | Flights | 96.6926 | 48 | 2.0144
Eastington | Goods & services | Purchase of goods | 160.9831 | 48 | 3.3538
Eastington | Goods & services | Use of services | 52.443 | 48 | 1.0926
Eastington | Goods & services | Other | 89.8008 | 48 | 1.8709
Eastington | Food & diet | Meat & fish | 90.2528 | 48 | 1.8803
Eastington | Food & diet | Other | 76.7768 | 48 | 1.5995
Eastington | Waste | Waste | 9.9861 | 48 | 0.20804
Ebley | Housing | Mains gas | 2863.2354 | 1508 | 1.8987
Ebley | Housing | Electricity | 1444.2513 | 1508 | 0.95773
Ebley | Housing | Oil | 3.9973 | 1508 | 0.0026508
Ebley | Housing | LPG | 2.508 | 1508 | 0.0016631
Ebley | Housing | Biomass | 12.5822 | 1508 | 0.0083436
Ebley | Housing | Coal | 19.7186 | 1508 | 0.013076
Ebley | Travel | Private | 2235.425 | 1508 | 1.4824
Ebley | Travel | Public | 657.3143 | 1508 | 0.43588
Ebley | Travel | Flights | 1273.1703 | 1508 | 0.84428
Ebley | Goods & services | Purchase of goods | 4561.7554 | 1508 | 3.025
Ebley | Goods & services | Use of services | 1824.5624 | 1508 | 1.2099
Ebley | Goods & services | Other | 1638.9066 | 1508 | 1.0868
Ebley | Food & diet | Meat & fish | 2917.5632 | 1508 | 1.9347
Ebley | Food & diet | Other | 2306.0967 | 1508 | 1.5292
Ebley | Waste | Waste | 351.8821 | 1508 | 0.23334
Lower Gloucester and Sharpness | Housing | Mains gas | 6.6858 | 234 | 0.028572
Lower Gloucester and Sharpness | Housing | Electricity | 316.2762 | 234 | 1.3516
Lower Gloucester and Sharpness | Housing | Oil | 1101.3193 | 234 | 4.7065
Lower Gloucester and Sharpness | Housing | LPG | 162.01 | 234 | 0.69235
Lower Gloucester and Sharpness | Housing | Biomass | 12.2664 | 234 | 0.052421
Lower Gloucester and Sharpness | Housing | Coal | 17.4778 | 234 | 0.074691
Lower Gloucester and Sharpness | Travel | Private | 568.301 | 234 | 2.4286
Lower Gloucester and Sharpness | Travel | Public | 140.2059 | 234 | 0.59917
Lower Gloucester and Sharpness | Travel | Flights | 446.8717 | 234 | 1.9097
Lower Gloucester and Sharpness | Goods & services | Purchase of goods | 894.8782 | 234 | 3.8243
Lower Gloucester and Sharpness | Goods & services | Use of services | 299.1544 | 234 | 1.2784
Lower Gloucester and Sharpness | Goods & services | Other | 358.643 | 234 | 1.5327
Lower Gloucester and Sharpness | Food & diet | Meat & fish | 508.5776 | 234 | 2.1734
Lower Gloucester and Sharpness | Food & diet | Other | 438.0234 | 234 | 1.8719
Lower Gloucester and Sharpness | Waste | Waste | 60.0197 | 234 | 0.25649
Ryeford | Housing | Mains gas | 464.9558 | 165 | 2.8179
Ryeford | Housing | Electricity | 161.5206 | 165 | 0.97891
Ryeford | Housing | Oil | 7.4272 | 165 | 0.045013
Ryeford | Housing | LPG | 0 | 165 | 0
Ryeford | Housing | Biomass | 1.402 | 165 | 0.008497
Ryeford | Housing | Coal | 0 | 165 | 0
Ryeford | Travel | Private | 273.992 | 165 | 1.6606
Ryeford | Travel | Public | 76.2853 | 165 | 0.46234
Ryeford | Travel | Flights | 214.4779 | 165 | 1.2999
Ryeford | Goods & services | Purchase of goods | 625.4743 | 165 | 3.7908
Ryeford | Goods & services | Use of services | 232.5597 | 165 | 1.4095
Ryeford | Goods & services | Other | 222.0372 | 165 | 1.3457
Ryeford | Food & diet | Meat & fish | 361.3768 | 165 | 2.1902
Ryeford | Food & diet | Other | 309.9582 | 165 | 1.8785
Ryeford | Waste | Waste | 42.3123 | 165 | 0.25644
Saul and Frampton | Housing | Mains gas | 0 | 141 | 0
Saul and Frampton | Housing | Electricity | 174.246 | 141 | 1.2358
Saul and Frampton | Housing | Oil | 739.7565 | 141 | 5.2465
Saul and Frampton | Housing | LPG | 8.192 | 141 | 0.058099
Saul and Frampton | Housing | Biomass | 10.1454 | 141 | 0.071953
Saul and Frampton | Housing | Coal | 1.1721 | 141 | 0.0083126
Saul and Frampton | Travel | Private | 321.552 | 141 | 2.2805
Saul and Frampton | Travel | Public | 81.1693 | 141 | 0.57567
Saul and Frampton | Travel | Flights | 270.4438 | 141 | 1.918
Saul and Frampton | Goods & services | Purchase of goods | 483.1574 | 141 | 3.4266
Saul and Frampton | Goods & services | Use of services | 162.9436 | 141 | 1.1556
Saul and Frampton | Goods & services | Other | 219.6581 | 141 | 1.5579
Saul and Frampton | Food & diet | Meat & fish | 280.8505 | 141 | 1.9918
Saul and Frampton | Food & diet | Other | 236.1028 | 141 | 1.6745
Saul and Frampton | Waste | Waste | 31.6056 | 141 | 0.22415
Sharpness | Housing | Mains gas | 252.4898 | 112 | 2.2544
Sharpness | Housing | Electricity | 114.511 | 112 | 1.0224
Sharpness | Housing | Oil | 0 | 112 | 0
Sharpness | Housing | LPG | 4.59 | 112 | 0.040982
Sharpness | Housing | Biomass | 0.51579 | 112 | 0.0046053
Sharpness | Housing | Coal | 0.34473 | 112 | 0.0030779
Sharpness | Travel | Private | 252.375 | 112 | 2.2533
Sharpness | Travel | Public | 58.9513 | 112 | 0.52635
Sharpness | Travel | Flights | 133.1404 | 112 | 1.1888
Sharpness | Goods & services | Purchase of goods | 311.7988 | 112 | 2.7839
Sharpness | Goods & services | Use of services | 110.0459 | 112 | 0.98255
Sharpness | Goods & services | Other | 72.0205 | 112 | 0.64304
Sharpness | Food & diet | Meat & fish | 214.1538 | 112 | 1.9121
Sharpness | Food & diet | Other | 165.9888 | 112 | 1.482
Sharpness | Waste | Waste | 28.9289 | 112 | 0.25829
Stonehouse | Housing | Mains gas | 2966.5788 | 1364 | 2.1749
Stonehouse | Housing | Electricity | 1334.1861 | 1364 | 0.97814
Stonehouse | Housing | Oil | 0 | 1364 | 0
Stonehouse | Housing | LPG | 21.983 | 1364 | 0.016117
Stonehouse | Housing | Biomass | 14.3749 | 1364 | 0.010539
Stonehouse | Housing | Coal | 18.1328 | 1364 | 0.013294
Stonehouse | Travel | Private | 1953.225 | 1364 | 1.432
Stonehouse | Travel | Public | 571.65 | 1364 | 0.4191
Stonehouse | Travel | Flights | 1279.6433 | 1364 | 0.93815
Stonehouse | Goods & services | Purchase of goods | 4283.3745 | 1364 | 3.1403
Stonehouse | Goods & services | Use of services | 1662.1762 | 1364 | 1.2186
Stonehouse | Goods & services | Other | 1633.3873 | 1364 | 1.1975
Stonehouse | Food & diet | Meat & fish | 2675.2977 | 1364 | 1.9614
Stonehouse | Food & diet | Other | 2147.0235 | 1364 | 1.5741
Stonehouse | Waste | Waste | 318.2175 | 1364 | 0.2333
Stroud | Housing | Mains gas | 4438.8868 | 2191 | 2.026
Stroud | Housing | Electricity | 2105.2138 | 2191 | 0.96085
Stroud | Housing | Oil | 53.9395 | 2191 | 0.024619
Stroud | Housing | LPG | 18.552 | 2191 | 0.0084674
Stroud | Housing | Biomass | 38.9468 | 2191 | 0.017776
Stroud | Housing | Coal | 18.8567 | 2191 | 0.0086064
Stroud | Travel | Private | 3085.876 | 2191 | 1.4084
Stroud | Travel | Public | 948.424 | 2191 | 0.43287
Stroud | Travel | Flights | 1952.2883 | 2191 | 0.89105
Stroud | Goods & services | Purchase of goods | 6600.762 | 2191 | 3.0127
Stroud | Goods & services | Use of services | 2789.6253 | 2191 | 1.2732
Stroud | Goods & services | Other | 2385.9499 | 2191 | 1.089
Stroud | Food & diet | Meat & fish | 4094.8508 | 2191 | 1.8689
Stroud | Food & diet | Other | 3243.2455 | 2191 | 1.4803
Stroud | Waste | Waste | 472.3332 | 2191 | 0.21558
Thrupp | Housing | Mains gas | 1245.9898 | 558 | 2.233
Thrupp | Housing | Electricity | 541.0195 | 558 | 0.96957
Thrupp | Housing | Oil | 40.7384 | 558 | 0.073008
Thrupp | Housing | LPG | 0 | 558 | 0
Thrupp | Housing | Biomass | 13.112 | 558 | 0.023498
Thrupp | Housing | Coal | 11.2037 | 558 | 0.020078
Thrupp | Travel | Private | 823.864 | 558 | 1.4765
Thrupp | Travel | Public | 241.3844 | 558 | 0.43259
Thrupp | Travel | Flights | 586.8067 | 558 | 1.0516
Thrupp | Goods & services | Purchase of goods | 1765.9908 | 558 | 3.1649
Thrupp | Goods & services | Use of services | 704.8487 | 558 | 1.2632
Thrupp | Goods & services | Other | 586.3852 | 558 | 1.0509
Thrupp | Food & diet | Meat & fish | 1067.8216 | 558 | 1.9137
Thrupp | Food & diet | Other | 866.9048 | 558 | 1.5536
Thrupp | Waste | Waste | 120.9659 | 558 | 0.21678
Upper Eastern Valley | Housing | Mains gas | 0 | 17 | 0
Upper Eastern Valley | Housing | Electricity | 30.2137 | 17 | 1.7773
Upper Eastern Valley | Housing | Oil | 159.0797 | 17 | 9.3576
Upper Eastern Valley | Housing | LPG | 0 | 17 | 0
Upper Eastern Valley | Housing | Biomass | 2.0772 | 17 | 0.12219
Upper Eastern Valley | Housing | Coal | 0 | 17 | 0
Upper Eastern Valley | Travel | Private | 47.378 | 17 | 2.7869
Upper Eastern Valley | Travel | Public | 10.9731 | 17 | 0.64548
Upper Eastern Valley | Travel | Flights | 41.4813 | 17 | 2.4401
Upper Eastern Valley | Goods & services | Purchase of goods | 83.0038 | 17 | 4.8826
Upper Eastern Valley | Goods & services | Use of services | 25.7396 | 17 | 1.5141
Upper Eastern Valley | Goods & services | Other | 17.7697 | 17 | 1.0453
Upper Eastern Valley | Food & diet | Meat & fish | 37.5483 | 17 | 2.2087
Upper Eastern Valley | Food & diet | Other | 38.1604 | 17 | 2.2447
Upper Eastern Valley | Waste | Waste | 3.8091 | 17 | 0.22407
Upper Gloucester and Sharpness | Housing | Mains gas | 663.9876 | 381 | 1.7427
Upper Gloucester and Sharpness | Housing | Electricity | 301.5036 | 381 | 0.79135
Upper Gloucester and Sharpness | Housing | Oil | 62.3044 | 381 | 0.16353
Upper Gloucester and Sharpness | Housing | LPG | 3.924 | 381 | 0.010299
Upper Gloucester and Sharpness | Housing | Biomass | 0.85809 | 381 | 0.0022522
Upper Gloucester and Sharpness | Housing | Coal | 0 | 381 | 0
Upper Gloucester and Sharpness | Travel | Private | 705.633 | 381 | 1.8521
Upper Gloucester and Sharpness | Travel | Public | 183.0426 | 381 | 0.48043
Upper Gloucester and Sharpness | Travel | Flights | 474.2125 | 381 | 1.2447
Upper Gloucester and Sharpness | Goods & services | Purchase of goods | 1389.0869 | 381 | 3.6459
Upper Gloucester and Sharpness | Goods & services | Use of services | 506.4313 | 381 | 1.3292
Upper Gloucester and Sharpness | Goods & services | Other | 528.7873 | 381 | 1.3879
Upper Gloucester and Sharpness | Food & diet | Meat & fish | 820.725 | 381 | 2.1541
Upper Gloucester and Sharpness | Food & diet | Other | 698.7202 | 381 | 1.8339
Upper Gloucester and Sharpness | Waste | Waste | 94.5078 | 381 | 0.24805
Western Stroudwater | Housing | Mains gas | 16.5661 | 18 | 0.92034
Western Stroudwater | Housing | Electricity | 20.6974 | 18 | 1.1499
Western Stroudwater | Housing | Oil | 54.3837 | 18 | 3.0213
Western Stroudwater | Housing | LPG | 0 | 18 | 0
Western Stroudwater | Housing | Biomass | 0.9253 | 18 | 0.051405
Western Stroudwater | Housing | Coal | 0 | 18 | 0
Western Stroudwater | Travel | Private | 49.017 | 18 | 2.7232
Western Stroudwater | Travel | Public | 11.1001 | 18 | 0.61667
Western Stroudwater | Travel | Flights | 38.5724 | 18 | 2.1429
Western Stroudwater | Goods & services | Purchase of goods | 68.6644 | 18 | 3.8147
Western Stroudwater | Goods & services | Use of services | 22.8508 | 18 | 1.2695
Western Stroudwater | Goods & services | Other | 20.2411 | 18 | 1.1245
Western Stroudwater | Food & diet | Meat & fish | 34.2947 | 18 | 1.9053
Western Stroudwater | Food & diet | Other | 30.9551 | 18 | 1.7197
Western Stroudwater | Waste | Waste | 3.2944 | 18 | 0.18302
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Carbon Reduction Opportunities
Housing
Emissions in this category include those that arise as a result of the use of energy by residents in their homes for heating and for power. Where housing emissions form a larger than average proportion of total emissions, this might be due to characteristics of the local housing stock that make homes harder to heat (e.g. where properties are of lower energy efficiency standards or where they are particularly large), or to heating system type, or alternatively it could indicate that members of the community might have less disposable income to spend on other goods and services and need to spend a higher proportion of their income on ensuring that their home stays warm. Possible measures to reduce carbon emissions from housing: Targeted retrofit programmes, particularly in areas where housing stock is older or of poor quality, and where settlements are off-gas and currently reliant on fossil fuel-based heating systems. This might include incentives and support to improve insulation and to switch to low carbon heating systems such as air source heat pumps. High standards for new development. Any new development within the canal areas will lead to an increase in the total footprint for that area unless net zero design standards are implemented. These might be in the form of carbon targets (e.g. a percentage reduction over Building Regulations) or operational energy use intensity targets. Stringent standards will require consideration of built form and orientation, passive heating and cooling methods, low carbon heating systems and building-mounted renewable technologies. Installation of small-scale local renewable and low carbon technologies to generate and distribute power and/or heat locally and reduce demand on the electricity grid (this might include district or community heating schemes where the central plant is low carbon). Larger-scale grid-connected renewable installations such as solar farms will not directly reduce emissions locally, but will contribute to the decarbonisation of the national grid and will therefore indirectly reduce emissions across all categories. Green infrastructure. Incorporation of green infrastructure can help to reduce the demand for cooling in buildings by providing shading. Green and blue infrastructure also help to sequester carbon, however these benefits are not specific to this category. Engagement with residents and active local groups on home energy saving and decarbonisation initiatives. This might include providing energy advice and outreach, and signposting to sources of support. For example, this might include guidance to help residents to sensitively retrofit homes of heritage value, or to access demand flexibility services such as time of use tariffs. Across the whole of the Stroud district, housing emissions account for 23% of total emissions, which is slightly higher than the national average (22%). Stroud canal areas with a particularly high proportion of housing-related emissions include the Upper Eastern Valley (39%), Lower Gloucester and Sharpness (30%) and Saul and Frampton (31%).
Travel
These are emissions resulting from the transport choices and behaviours of residents. High travel-related emissions might be an indicator of rurality, where longer distances are required to travel to amenities, and where reliance on car travel is often higher. It might also reflect the type and size of vehicles purchased by residents or frequent international travel. Possible measures to reduce carbon emissions from travel: Minimising the need for travel. This might include, for example, higher density development or the provision of local amenities. Provision of safe, practical and attractive routes for active travel to help to reduce reliance on cars. Encourage use of public transport by ensuring adequate and appropriate provision (in terms of route planning, interconnectivity, accessibility, frequency of service etc.). Electric vehicle charging infrastructure. A coordinated roll-out of public charging infrastructure can help to encourage drivers to switch to an electric vehicle. Travel-related emissions make up approximately 20% of the carbon footprint of the Stroud district, which equates to 3.69 tonnes CO2 per year per household. This is higher than the national average of 3.2 tonnes CO2 per year. Stroud canal areas with the highest high proportion of travel-related emissions are Sharpness (26%), Western Stroudwater (27%) and Eastington (24%).
Goods and services,
These emissions are those that arise from the purchase of goods (except food) and the use of services by residents. This refers to all household goods such as homeware, toiletries, medicines, furnishings, electronic goods and appliances, as well as large items such as cars. Services include the maintenance and repair of homes, vehicles and other equipment, banking and insurance, medical services, treatments, education costs, communications (e.g. TV, internet and phone contracts), and other fees and subscriptions. Leisure, entertainment, sporting or social activities also come into this category. High emissions in this sector might reflect an affluent population with a high level of disposable income. Possible measures to reduce carbon emissions from the consumption of goods and services: Reducing emissions from council operations will help to lower the emissions associated with residents’ use of council-run services. This might include the electrification of council-owned fleets, improved energy performance of council-owned properties, and a procurement policy that requires council suppliers (including public transport providers) to monitor and reduce their own carbon emissions. Behaviour change campaigns to help residents to understand the impact of their own consumption behaviours on their carbon footprint, and the provision of information. Engagement with local businesses and service providers to help them to reduce emissions, for example through energy efficiency initiatives or by switching to a green tariff. Emissions from the consumption of goods and services in the Stroud district makes up 34% of the total footprint, which equates to an average of 6.1 tonnes of CO2 per year per household. The national average is 5.57 tonnes CO2 per year for this category. Canal areas with the highest emissions in this category include Upper Eastern Valley (7.4 t/CO2/yr/household), Chalford (7.0 tCO2/yr/household), and Brimscombe (6.8 tCO2/yr/household). Only Ebley, Stroud and Thrupp have emissions below the national average.
Food and diet
These are emissions resulting from the consumption of food and drink products by residents. Emissions in this sector are largely dependent on purchasing decisions made by residents. Possible measures to reduce carbon emissions from food and diet: Encourage the consumption of locally-produced goods. This might include goods from local growers or grow-your-own (e.g. allotment provision), and perhaps inclusion of spaces for markets for local produce. Behaviour change campaigns to encourage reduced consumption of meat, particularly where not sourced locally or raised organically. It is important that campaigns around dietary changes are sensitive to concerns about farmer’s livelihoods. Campaigns could also target reductions in food waste. Land use. Consider working with local farmers to help them to reduce emissions from their own operations and to identify opportunities for selling products locally. Emissions from food and diet in the Stroud district are slightly higher than the national average (3.85 tCO2/yr compared to 3.69 tCO2/yr per household). Canal areas with the highest emissions in this category include Upper Eastern Valley (4.5 tCO2/yr/household), Brimscombe, Chalford and Ryeford (all 4.1 tCO2/yr/household), and Lower and Upper Gloucester and Sharpness (both 4.0 tCO2/yr/household).
Waste
These emissions are associated with the management of waste generated by residents. Possible measures to reduce carbon emissions from waste: Local authority waste management policies. This could include the provision of recycling facilities and regular collections and consideration of waster as a resources within the circular economy Behaviour change campaigns to encourage waste reduction (from purchasing decisions to efficient use of resources in the home) and increase recycling rates at household level. Emissions from waste make up around 1-2% of total emissions across all canal areas and are very slightly higher than the national average.